## Read me
Module 9 · Harbourview AI cost model · starter workbook
Harbourview Polyclinics and all figures are fictional, for teaching. S$ = Singapore dollars.
HOW TO USE THIS WORKBOOK
1. Inputs: every case figure, in blue, with its source in the case pack. Change an input and the whole model should follow.
2. Model A (medicine questions assistant) and Model C (consultation note drafter): fill every YELLOW cell with a formula that refers to Inputs.
Row 6 on each model sheet is a worked example showing the expected style. Never type a result as a number.
3. Each model sheet has a price multiplier cell (C3). Set it to 0.5, 1 or 1.5 to see the price scenarios.
4. Scenarios: fill the two 3 x 3 grids of net value a month. Hint: write each cell as one formula, or copy a model sheet once per price level.
5. Levers: work out the cost per question with your chosen levers and compare it with the S$1,500 cap.
6. Checks: compares your base-case results (30% adoption, today's prices, case defaults) with the expected figures. Aim for every row to say OK.
7. Sensitivity: vary at least three assumptions per initiative from low to high and record the net value.
COLOUR KEY
Blue text = input you may change · Black = formula · Green = link to another sheet · Yellow fill = cell for you to complete
The shared rules are in case section 6 on the Module 9 page. You may change an assumption if you say why; keep the shared-rule result alongside.

## Inputs
Inputs · every figure from the case pack
Input | Value | Unit | Source in the case pack
— Shared —
Budget, year from 1 April | 450000 | S$ | Case 1 · CFO rule 1
Realisation rate for freed staff time | 30% | share | Case 1 · CFO rule 3
Medicine assistant cap: model + database a month | 1500 | S$ | Case 1 · CFO rule 4
Price scenario: lower | 0.5 | x | Case 1 · CFO rule 5
Price scenario: higher | 1.5 | x | Case 1 · CFO rule 5
Adoption scenario 1 | 10% | share | CFO memo
Adoption scenario 2 | 30% | share | CFO memo
Adoption scenario 3 | 60% | share | CFO memo
— Medicine questions assistant (A) —
Eligible patients, nine clinics | 120000 | patients | Case 2
Questions per active user a month | 1.4 | questions | Case 2 · pilot
Input tokens: instructions (same every time) | 1100 | tokens | Case 2 · costs
Input tokens: prescription summary | 400 | tokens | Case 2 · costs
Input tokens: question and recent messages | 160 | tokens | Case 2 · costs
Input tokens: three leaflet passages | 1600 | tokens | Case 2 · costs
Output tokens per answer | 250 | tokens | Case 2 · costs
Standard model: input price per million tokens | 4 | S$ | Case 4
Standard model: output price per million tokens | 20 | S$ | Case 4
Share of answers checked by the judge | 20% | share | Case 2 · costs
Judge input tokens per check | 1600 | tokens | Case 2 · costs
Judge output tokens per check | 60 | tokens | Case 2 · costs
Platform, hosting and monitoring a month | 2500 | S$ | Case 2 · costs
Leaflet search database a month | 300 | S$ | Case 2 · costs
Pharmacist safety review hours a month | 26 | hours | Case 2 · costs
Employed pharmacist cost an hour | 60 | S$ | Case 2
Agency pharmacist cost an hour | 70 | S$ | Case 2
Agency hours bought a month (cash-releasing ceiling) | 300 | hours | Case 2
Helpline calls avoided per active user a month | 0.1 | calls | Case 2 · pilot, measured at 23% adoption
Pharmacist minutes per routine call | 6 | minutes | Case 2
Handover rate (share of questions) | 12% | share | Case 2 · build 1.1; build 1.2 aims for 8%
Pharmacist minutes per written handover reply | 2.5 | minutes | Case 2
Spare written-message capacity a day | 180 | messages | Case 2
One-off rollout cost | 90000 | S$ | Case 2 · costs
— Consultation note drafter (C) —
Doctor consultations a month, all clinics | 95000 | consultations | Case 3
Patients agreeing to recording | 85% | share | Case 3 · pilot
Doctors | 260 | doctors | Case 3
Minutes saved per drafted note | 1.5 | minutes | Case 3 · pilot of six volunteers; reference sites 1.0
Doctor cost an hour | 150 | S$ | Case 3
Price plan: 1 = per note, 2 = per seat, 3 = per accepted note | 1 | choice | Your choice · case 3
Per note price | 0.38 | S$ | Case 3 · plans
Per seat price a month | 40 | S$ | Case 3 · plans
Minimum seats | 50 | seats | Case 3 · plans
Price per accepted note | 0.65 | S$ | Case 3 · plans
Share of drafts accepted (fewer than 20% of words changed) | 58% | share | Case 3 · pilot
Share of drafted notes audited | 2% | share | Case 3 · costs
Doctor minutes per audit | 5 | minutes | Case 3 · costs
Devices support and monitoring a month | 1500 | S$ | Case 3 · costs
One-off rollout cost | 260000 | S$ | Case 3 · costs

## Model A
Model A · medicine questions assistant
Price multiplier for this sheet (0.5, 1 or 1.5) |  | 1
Line | Unit | Adoption 1 | Adoption 2 | Adoption 3 | Hint (how the shared rule works)
Adoption | share | 10% | 30% | 60%
Active users | users | 12000 | 36000 | 72000 | Eligible patients × adoption (worked example)
Questions a month | questions |  |  |  | Active users × questions per active user
Assistant cost per question | S$ |  |  |  | (input tokens × input price + output tokens × output price) ÷ 1,000,000 × price multiplier
Judge cost per question | S$ |  |  |  | Share judged × judge tokens cost × price multiplier
Model cost a month | S$ |  |  |  | Questions × (assistant + judge cost per question)
Fixed cost a month | S$ |  |  |  | Platform + database + safety review hours × pharmacist rate
Running cost a month | S$ |  |  |  | Model + fixed
Pharmacist hours saved a month | hours |  |  |  | (users × calls avoided × minutes per call − questions × handover rate × minutes per reply) ÷ 60
Value a month | S$ |  |  |  | First 300 hours are cash at the agency rate; beyond that, pharmacist rate × realisation; negative hours cost the agency rate
Net value a month | S$ |  |  |  | Value − running cost
First-year cost | S$ |  |  |  | One-off + 12 × running cost
Fits the budget? | yes/no |  |  |  | Compare with the budget input
Payback | months |  |  |  | One-off ÷ net value a month, only if net is positive
Handovers a day | messages |  |  |  | Questions × handover rate ÷ 30; compare with spare capacity
Model + database a month | S$ |  |  |  | Compare with the S$1,500 cap
Running cost per active user | S$ |  |  |  | Running cost ÷ active users

## Model C
Model C · consultation note drafter
Price multiplier for this sheet (0.5, 1 or 1.5) |  | 1
Line | Unit | Adoption 1 | Adoption 2 | Adoption 3 | Hint (how the shared rule works)
Adoption | share | 10% | 30% | 60%
Doctors using it | doctors | 26 | 78 | 156 | Doctors × adoption, rounded up (worked example)
Drafted notes a month | notes |  |  |  | Consultations × adoption × consent rate
Licence a month | S$ |  |  |  | Depends on the plan input: per note; larger of minimum seats and doctors × seat price; notes × accepted share × outcome price. × price multiplier
Clinical audit a month | S$ |  |  |  | Notes × share audited × minutes ÷ 60 × doctor rate
Running cost a month | S$ |  |  |  | Licence + audit + devices support
Running cost per note | S$ |  |  |  | Running cost ÷ notes
Doctor hours freed a month | hours |  |  |  | Notes × minutes saved ÷ 60
Value a month | S$ |  |  |  | Hours × doctor rate × realisation rate (capacity, not cash)
Net value a month | S$ |  |  |  | Value − running cost
First-year cost | S$ |  |  |  | One-off + 12 × running cost
Fits the budget? | yes/no |  |  |  | Compare with the budget input
Payback | months |  |  |  | One-off ÷ net value a month, only if net is positive

## Scenarios
Scenarios · net value a month (S$)
Rows: adoption. Columns: price multiplier. Each cell must be a formula, so the grid follows the inputs.
Medicine questions assistant
Adoption | Price × lower | Price × 1 | Price × higher
Multiplier | 0.5 | 1 | 1.5
10%
30%
60%
Consultation note drafter (plan as set on Inputs)
Adoption | Price × lower | Price × 1 | Price × higher
Multiplier | 0.5 | 1 | 1.5
10%
30%
60%

## Levers
Levers · medicine assistant cost per question
Set each lever to 1 (on) or 0 (off). Fill the yellow cells with formulas. Case section 4 gives the provider terms.
Lever input | Value | Note
Cache the instructions (1/0) | 0
Share of questions reusing the cache | 90%
Cache read price as share of input price | 10%
Cache write price as share of input price | 125%
Two passages instead of three (1/0) | 0
Cap answers at 180 tokens (1/0) | 0
Capped output tokens | 180
Route routine questions to the small model (1/0) | 0
Share of questions routed | 50%
Small model price as share of standard | 20%
Router input tokens on the small model | 300
Small model input price per million | 0.8
Run the judge as a batch at half price (1/0) | 0
Result | Value | Hint
Assistant cost per question with levers |  | Instructions (cached or not) + other input + output; then the routed share at the small model price plus the router
Judge cost per question with levers |  | Judge cost, halved if batched
Total cost per question |  | Assistant + judge
Model + database a month at adoption scenario 3, today's prices |  | Questions at scenario 3 × total cost per question + database; compare with the cap
Same, prices at the higher scenario |  | Multiply the token part by the higher price multiplier

## Sensitivity
Sensitivity · what swings the answer (adoption scenario 2, today's prices)
Change one input at a time on Inputs, record the net value a month, then put the input back. Add your own rows.
Initiative | Assumption | Low value | Net value at low | High value | Net value at high | Range (S$) | Crosses zero?
A | Model price multiplier | 0.5 |  | 1.5
A | Handover rate | 0.16 |  | 0.08
A | Calls avoided per active user | 0.07 |  | 0.13
C | Minutes saved per note | 1 |  | 2
C | Realisation rate | 0.1 |  | 0.5
C | Licence price multiplier | 0.5 |  | 1.5

## Checks
Checks · base case (adoption scenario 2 = 30%, price multiplier 1, case inputs, per-note plan)
Set Inputs back to the case figures and both price multipliers to 1. Every row should say OK. Expected values come from the course team's reference model.
Check | Your result | Expected | Difference | Status
Assistant: cost per question (assistant + judge) | 0 | 0.01956 | -0.01956 | Not yet
Assistant: running cost a month | 0 | 5345.824 |  | Not yet
Assistant: pharmacist hours saved a month | 0 | 108 |  | Not yet
Assistant: value a month | 0 | 7560 |  | Not yet
Assistant: net value a month | 0 | 2214.176 |  | Not yet
Assistant: handovers a day | 0 | 201.6 |  | Not yet
Drafter: drafted notes a month | 0 | 24225 |  | Not yet
Drafter: licence a month (per-note plan) | 0 | 9205.5 |  | Not yet
Drafter: clinical audit a month | 0 | 6056.25 |  | Not yet
Drafter: value a month | 0 | 27253.125 |  | Not yet
Drafter: net value a month | 0 | 10491.375 |  | Not yet